## Slide 1: Community Pharmacy and General Practice Engagement and Integration Project Update
Chris Lawson, Richard Daniszewski, Erica Carmody, Cheryl Markey, Claire Pendleton, Caitlin Smith, Christian Taylor, Fiona Bankes

## Slide 2: NHS North East Yorkshire Leadership Academy (NEYLA) Primary Care Collaborative
Jan-May 2024- Team Across Barnsley Primary Care Taking Part in a Series of Learning Sessions and Co-Labs Looking at How We can: - Improve Engagement between CP and GP - Improve Communication between CP and GP - Improve Collaboration between CP and GP
Looking at: What Now? Near Future? What’s Over The Hill?
Priorities for Near Future We are Focussing On
- CP/GP Engagement
- Communications and Pharmacy First

## Slide 3: Community Pharmacy & GP Communications Pilot
Pilot between Ashville Medical Centre and Lo’s Pharmacy Oaks Park (Feb 2024)
NHS Mail became main method of communication, with email subject highlighting level of priority
Feedback from GP Practice and Pharmacy - Very positive
Pharmacy comment - Emails getting handled smoothly and promptly
Acknowledgement that the same approach may not work everywhere
Work continuing - other alternatives being considered – eg AccuRx, GP Connect

## Slide 4: Pharmacy First - Barnsley Support
Service Launched 31st January 2024
To determine Readiness, Awareness and Plans in relation to Pharmacy First, NHS Barnsley ICB/PCN Meds Optimisation Team contacted:
  Barnsley Community Pharmacies
  Barnsley General Practices
When information received back centrally:
  Team created a Plan based on feedback from pharmacies and GP practices
  Various challenges were identified

## Slide 5: Challenges
Short NHSE timeframe to launch led to lack of:
  Time to prepare for the launch of the Scheme
  Initial support, equipment and training for the Community Pharmacies
  Initial support for GP Practices
  Awareness in GP Practice about Pharmacy First
Further challenges highlighted during the project:
  Finding the right staff in GP Practice to liaise with
  One “negative” Pharmacy First experience can impact on referrals – CPs, GPs and Patients
  National Pharmacy IT Issues e.g. Pharmrefer MFA, GP Connect Access and Update delays

## Slide 6: Wider Stakeholder Engagement
Working Closely with CPSY
Working Closely with ICB Community Pharmacy Clinical Lead
Attending SY Pharmacy First Steering Group meetings
Attended Barnsley GP Practice Manager Meeting Mar. 2024 with SY ICB Community Pharmacy Clinical Lead

## Slide 7: Development of a Pharmacy First Resource for GP Reception Staff
Aim to respond to some of the feedback received initially from Community Pharmacies
Tailor the Referral Tool to Locally Agreed Pharmacy and GP Practice Conditions
Develop an Agreement of How the Service Will work incl. Escalations and Referrals
Work Together to Develop Key Information for GP Practice Staff
Has the GP Practice Got A Copy of CPCS/Pharmacy First-Referral Tool?

## Slide 8: The Resource

## Slide 9: Where Are We Now-Pharmacy First?
Reaching out to Community Pharmacy Contacts- Experience so far and Feedback
Reaching out to GP Practice Managers- Questionnaire
Internal feedback from GP Practice via ICB/PCN Medicines Optimisation Team Members
Collating GP Practice Pharmacy First Referral Data
Plan: to consider ways to increase the number of referrals made, where appropriate

## Slide 10: GP Practice Peer Support – Pharmacy First Referrals
Session held virtually
Informal session between four SystmOne Practices, led by one who is benefiting from referrals to community pharmacies via AccuRx
AccuRx introduced as a method for referrals
PharmRefer / multi-factoral authentication process seen as barrier
Initial feedback from the session was positive
Benefit seen in both referral data and local pharmacy feedback
Aim is to replicate across Barnsley

## Slide 11: ICB and Community Pharmacy South Yorkshire Working Group
Group set up between NHS South Yorkshire ICB and CPSY colleagues
Regular meetings to encourage an increase in referrals
NHS Barnsley ICB / PCN Medicines Optimisation team have good links with GP Practice teams and nearby pharmacies
Acknowledged the need to focus on 1/7 Clinical Pathways
Data showed potential for more UTI referrals
Currently identifying Practices in each SYICB Place to trial UTI focus
Progress to be evaluated once trial starts

## Slide 12: Can We Support You?
If you need any help or wish to feed back, please email:
Christian Taylor: christian.taylor@nhs.net
Claire Pendleton: claire.pendleton@nhs.net
Richard Daniszewski: richard.daniszewski@nhs.net
Laura Richardson: laurarichardson@cpsy.org.uk